Deterministic Scheduling
Krzysztof Giaro and Adam Nadolski
Gdańsk University of Technology

---
Lecture Plan
Introduction to deterministic scheduling
Critical path method
Some discrete optimization problems
Scheduling to minimize Cmax
Scheduling to minimize Ci
Scheduling to minimize Lmax
Scheduling to minimize the number of tardy tasks
Scheduling on dedicated processors

---
Introduction to Deterministic Scheduling
Our aim is to schedule the given set of tasks (programs, etc.) on machines (or processors).
We have to construct a schedule that fulfils given constraints and minimizes the optimality criterion.
Deterministic model: All the parameters of the system and of the tasks are known in advance.
Genesis and practical motivation:
scheduling manufacturing processes,
project planning,
school or conference timetabling,
scheduling processes in multitask operational systems,
distributed computing.

---
Introduction to Deterministic Scheduling
Example 1. Five tasks with processing times p1,...,p5=6,9,4,1,4 have to be processed on three processors to minimize schedule length.
Graphical representation of the schedule – Gantt chart
Why the above schedule is feasible?
General constraints in classical scheduling theory:
each task is processed by at most one processor at a time,
each processor is capable of processing at most one task at a time,
other constraints – to be discussed...

---
Introduction to Deterministic Scheduling
Processors characterization
Parallel processors (each processor is capable to process each task):
identical processors – every processor is of the same speed,
uniform processors – processors differ in their speed, but the speed does not depend on the task,
unrelated processors – the speed of the processor depend on the particular task processed.
Schedule on three parallel processors

---
Introduction to Deterministic Scheduling
Processors characterization
Dedicated processors
Each job consists of the set of tasks preassigned to processors (job Jj consists of tasks Tij preassigned to Pi, of processing time pij). The job is completed at the time the latest task is completed,
some jobs may not need all the processors (empty operations),
no two tasks of the same job can be scheduled in parallel,
a processor is capable to process at most one task at a time.
There are three models of scheduling on dedicated processors:
flow shop – all jobs have the same processing order through the machines coincident with machines numbering,
open shop – the sequence of tasks within each job is arbitrary ,
job shop – the machine sequence of each job is given and may differ between jobs.

---
Introduction to Deterministic Scheduling
Processors characterization
Dedicated processors – open shop
(processor sequence is arbitrary for each job).
Example. One day school timetable.
Teachers
Classes
M1	M2	M3
J1	3	2	1
J2	3	2	2
J3	1	1	2

---
Introduction to Deterministic Scheduling
Processors characterization
Dedicated processors – flow shop (processor sequence is the same for each job – task Tij must precede Tkj for i<k).
Example. Conveyor belt.
Dedicated processors will be considered later ...
Robots
Details
M1	M2	M3
Ja	3	2	1
Jb	3	2	2
Jc	1	1	2
Ja
Jb
Jc
M1
M2
M3

---
Introduction to Deterministic Scheduling
Tasks characterization
There are given: the set of n tasks T={T1,...,Tn} and the set of m machines (processors) M={M1,...,Mm}.
Task Tj :
Processing time. It is independent of processor in the case of identical processors and is denoted pj. In the case of uniform processors, processor Mi speed is denoted bi and the processing time of Tj on Mi is pj/bi. In the case of unrelated processors the processing time of Tj on Mi is pij.
Release (or arrival) time rj. The time at which the task is ready for processing. By default all release times are zero.
Due date dj. Specifies a time limit by which Tj should be completed. Usually, penalty functions are defined in accordance with due dates, or dj denotes the ‘hard’ time limit (deadline) by which Tj must be completed.
Weight wj – expresses the relative urgency of Tj , by default wj=1.

---
Introduction to Deterministic Scheduling
Tasks characterization
Dependent tasks:
In the task set there are some precedence constraints defined by a precedence relation. TiTj means that task Tj cannot be started until Ti is completed (e.g. Tj needs the results of Ti).
In the case there are no precedence constraints, we say that the tasks are independent (by default). In the other case we say that the tasks are dependent.
The precedence relation is usually represented as a directed graph in which nodes correspond to tasks and arcs represent precedence constraints (task-on-node graph). Transitive arcs are usually removed from precedence graph.

---
Introduction to Deterministic Scheduling
Tasks characterization
Example. A schedule for 10 dependent tasks (pj given in the nodes).
2
6
3
T5
1
1
2
3
1
T1
T2
T3
T4
T6
T7
T8
T9
T10
2
2

---
Introduction to Deterministic Scheduling
Tasks characterization
Example. A schedule for 10 dependent tasks (pj given in the nodes).
2
6
3
T5
1
1
2
3
1
T1
T2
T3
T4
T6
T7
T8
T9
T10
2
2

---
Introduction to Deterministic Scheduling
Tasks characterization
Example. A schedule for 10 dependent tasks (pj given in the nodes).
T1
2
T2
T3
T4
3
1
2
T6
T5
3
1
6
T8
T7
2
T10
1
T9
2

---
Introduction to Deterministic Scheduling
Tasks characterization
A schedule can be:
non-preemptive – preempting of any task is not allowed (default),
preemptive – each task may be preempted at any time and restarted later (even on a different processor) with no cost.
Preemptive schedule on parallel processors

---
Introduction to Deterministic Scheduling
Feasible schedule conditions (gathered):
each processor is assigned to at most one task at a time,
each task is processed by at most one machine at a time,
task Tj is processed completely in the time interval [rj,),
precedence constraints are satisfied,
in the case of non-preemptive scheduling no task is preempted, otherwise the number of preemptions is finite.

---
Introduction to Deterministic Scheduling
Optimization criteria
A location of the task Ti within the schedule:
completion time Ci
flow time Fi=Ci–ri,
lateness Li=Ci–di,
tardiness Di=max{Ci–di,0},
“tardiness flag” Ui=w(Ci>di), i.e. the answer (0/1, logical no/yes) to the question whether the task is late or not.

---
Introduction to Deterministic Scheduling
Optimization criteria
Most common optimization criteria:
schedule length (makespan) Cmax=max{Cj : j=1,...,n},
total completion time Cj = i=1,...,n Ci,
mean flow time F = (i=1,...,n Fi)/n.
Cmax = 9,
Cj = 6+9+4+7+8 = 34
A schedule on three parallel processors, p1,...,p5=6,9,4,1,4.
In the case there are tasks weights we can consider:
total weighted completion time wjCj = i=1,...,n wiCi,
w1,...,w5=1,2,3,1,1
wjCj = 6+18+12+7+8 = 51

---
Introduction to Deterministic Scheduling
Optimization criteria
Related to due times:
maximum lateness Lmax=max{Lj : j=1,...,n},
maximum tardiness Dmax=max{Dj : j=1,...,n},
total tardiness Dj = i=1,...,n Di,
number of tardy tasks Uj = i=1,...,n Ui,
weighted criteria may be considered, e.g. total weighted tardiness wjDj = i=1,...,n wiDi.
Li= –1 2 –1 2 0
Di= 0 2 0 2 0
Lmax = Dmax = 2
Dj = 4, Uj = 2
Task: T1 T2 T3 T4 T5
di= 7 7 5 5 8
Some criteria are pair-wise equivalent
Li = Ci –di, F= (Ci)/n – (ri)/n.

---
Introduction to Deterministic Scheduling
Classification of deterministic scheduling problems.
 |  | 
 is of the form:
P – identical processors
Q – uniform processors
R – unrelated processors
O – open shop
F – flow shop
PF – „permutation” flow shop
J – job shop
Moreover:
there may be specified the number of processors, e.g. O4,
in the case of single processors we just put 1,
we put ‘–’ in the case of processor-free environment.
Procession environment
Task characteristics
Optimization criterion

---
Introduction to Deterministic Scheduling
Classification of deterministic scheduling problems.
In the case  is empty all tasks characteristics are default: the tasks are non-preemptive, not depended, rj=0, processing times and due dates are arbitrary.
 possible values:
pmtn – preemptive tasks,
res – additional resources exist (omitted),
prec – there are precedence constraints,
rj – arrival times differ per task,
pj=1 or UET – all processing times equal to 1 unit,
pij{0,1} or ZUET – all tasks are of unit time or empty (dedicated processors),
Cjdj – dj denote deadlines,

---
Introduction to Deterministic Scheduling
Classification of deterministic scheduling problems.
 possible values:
in–tree, out–tree, chains ... – reflects the precedence constraints (prec).
out–tree
in–tree

---
Introduction to Deterministic Scheduling
Classification of deterministic scheduling problems.
Examples.
P3|prec|Cmax – scheduling non-preemptive tasks with precedence constraints on three parallel identical processors to minimize schedule length.
R|pmtn,prec,ri|Ui – scheduling preemptive dependent tasks with arbitrary ready times and arbitrary due dates on parallel unrelated processors to minimize the number of tardy tasks.
1|ri,Cidi|– – decision problem of existence (no optimization criterion) of schedule of independent tasks with arbitrary ready times and deadlines on a single processor, such that no task is tardy.

---
Introduction to Deterministic Scheduling
Properties of computer algorithm evaluating its quality.
Computational (time) complexity – function that estimates (upper bound) the worst–case operation number performed during execution in terms of input data size.
Polynomial (time) algorithm – when time complexity may be bounded by some polynomial of data size. In computing theory polynomial algorithms are considered as efficient.

---
Introduction to Deterministic Scheduling
Properties of computer algorithm evaluating its quality.
NP-hard problems are commonly believed not to have polynomial time algorithms solving them. For these problems we can only use fast but not accurate procedures or (for small instances) long time heuristics. NP-hardness is treated as computational intractability.
How to prove that problem A is NP-hard?
Sketch: Find any NP-hard problem B and show the efficient (polynomial) procedure that reduces (translates) B into A. Then A is not a less general problem than B, therefore if B was hard, so is A.

---
Introduction to Deterministic Scheduling
Reductions of scheduling problems
1
P
Pm
Q
Qm
R
Rm

pi=1

rj
wiFi
F
wiDi
Di
wiUi
Ui
Lmax
Cmax
prec
chain

out–tree
in–tree

---
Introduction to Deterministic Scheduling
Computational complexity of scheduling problems
If we restrict the number of processors to 1,2,3,, there are 4536 problems:
416 – polynomial-time solvable,
3817 – NP–hard,
303 – open.
How do we cope with NP–hardness?
polynomial-time approximate algorithms with guaranteed approximation ratio,
exact pseudo-polynomial time algorithms,
exact algorithms, efficient only in the mean-case,
heuristics (tabu-search, genetic algorithms, etc.),
in the case of small input data – exponential exhaustive search
(e.g. branch and bound).

---
Introduction to Deterministic Task Scheduling
General problem analysis schema
Optimization problem X
decision version Xd
Xd  P?  Xd  NPC?
Construct effective algorithm solving X
Xd  PseudoP?  Xd  NPC! ?
Construct pseudo-polynomial time algorithm for X
Do approximations satisfy us?
Yes
Polynomial-time
approximate algorithms
approximation schemas
No
Restrict problem X
Small data: exhaustive search (branch & bound)
Heuristics: tabu search, ...
Do not exist

---
Critical Path Method
–|prec|Cmax model consists of a set of dependent tasks of arbitrary lengths, which do not need processors. Our aim is to construct a schedule of minimum length.
Precedence relation  is a quasi order in the set of tasks, i.e. it is
anti-reflective: Ti TiTi
transitive Ti,Tj,Tk,(TiTj  TjTk)  TiTk

---
Critical Path Method
Precedence relation  is represented with an acyclic digraph:
nodes correspond to tasks, nodes weights are equal to processing times,
TiTj  there exists a directed path connecting node Ti and node Tj,
transitive arcs are removed
Example. Precedence relation for 19 tasks.
T1,3
T2,8
T3,2
T4,2
T5,4
T6,6
T7,9
T9,1
T10,2
T8,2
T11,1
T12,2
T14,5
T15,9
T13,6
T16,6
T17,2
T18,5
T19,3

---
Critical Path Method
–|prec|Cmax model consists of a set of dependent tasks of arbitrary lengths, which do not need processors. Our aim is to construct a schedule of minimum length.
The idea: for every task Ti we find the earliest possible start time l(Ti), i.e. the length of the longest path terminating at that task.
How to find these start times?
Critical Path Method:
1. find a topological node ordering (the start of any arc precedes its end),
2. assign l(Ta)=0 for every task Ta without predecessor,
3. assign l(Ti)=max{l(Tj)+pj: exists an arc (Tj,Ti)} to all other tasks in topological order.

---
Critical Path Method
0
0
0
T1:
T2:
T3:
T4:
T5:
T6:
T7:
T8:
T9:
T10:
T11:
T12:
T13:
T14:
T15:
T16:
T17:
T18:
T19:
Example. Construction of a schedule for 19 tasks
Starting
times
Topological
ordering
3
T1:0+3
3
T1:0+3
2
T3:0+2
2
T3:0+2
T4:3+2
5
8
T2:0+8, T5:3+4, T6:2+6
8
T2:0+8, T5:3+4, T6:2+6
11
T7:2+9
11
T7:2+9
9
T9:8+1, T8:5+2
12
T10:8+2, T11:11+1
12
T10:8+2, T11:11+1
12
T10:8+2, T11:11+1
13
T12:11+2
T13:9+6, T14:12+5
17
18
T16:12+6, T17:13+2
T1,3
T2,8
T3,2
T4,2
T5,4
T6,6
T7,9
T9,1
T10,2
T8,2
T11,1
T12,2
T14,5
T15,9
T13,6
T16,6
T17,2
T18,5
T19,3

---
Critical Path Method
T1,3
T2,8
T3,2
T4,2
T5,4
T6,6
T7,9
T9,1
T10,2
T8,2
T11,1
T12,2
T14,5
T15,9
T13,6
T16,6
T17,2
T18,5
T19,3
11
9
12
13
17
18
11
12
12
T1:
T2:
T3:
T4:
T5:
T6:
T7:
T8:
T9:
T10:
T11:
T12:
T13:
T14:
T15:
T16:
T17:
T18:
T19:
0
0
0
3
2
8
5
3
2
8

---
Critical Path Method
Critical Path Method does not only minimize Cmax, but also optimizes all previously defined criteria
We can introduce to the model arbitrary release times by adding for each task Tj extra task of length rj, preceding Tj.

---
Some Discrete Optimization Problems
maximum flow problem. There is given a loop-free multidigraph D(V,E) where each arc is assigned a capacity c:EN. There are two specified nodes – the source s and the sink t. The aim is to find a flow f:EN{0} of maximum value.
What is a flow of value F?
eE f(e)c(e), (flows may not exceed capacities)
vV–{s,t} e terminates at v f(e) – e starts at v f(e) = 0,
(the same flows in and flows out for every ‘ordinary’ node)
e terminates at t f(e) – e starts at t f(e) = F,
(F units flow out of the network through the sink)
e terminates at s f(e) – e starts at s f(e) = –F,
(F units flow into the network through the source)

---
Some Discrete Optimization Problems
maximum flow problem. There is given a loop-free multidigraph D(V,E) where each arc is assigned a capacity c:EN. There are two specified nodes – the source s and the sink t. The aim is to find a flow f:EN{0} of maximum value.
Network, arcs capacity
2
5
3
1
1
2
3
2
2
1
1
4
S
T

---
Some Discrete Optimization Problems
maximum flow problem. There is given a loop-free multidigraph D(V,E) where each arc is assigned a capacity c:EN. There are two specified nodes – the source s and the sink t. The aim is to find a flow f:EN{0} of maximum value.
... and maximum flow F=5
Complexity O(|V||E|log(|V|2/|E|))  O(|V|3).
2/2
5/2
3/2
1/0
1/0
2/2
3/1
2/2
2/1
1/1
1/1
4/1
S
T

---
Some Discrete Optimization Problems
Many graph coloring models.
Longest (shortest) path problems.
Linear programming – polynomial-time algorithm known.
The problem of graph matching. There is a given graph G(V,E) with a weight function w:EN{0}. A matching is a subset AE of pair-wise non-neighboring edges.
Maximum matching: find a matching of the maximum possible cardinality ((L(G))). The complexity O(|E||V|1/2).
Heaviest (lightest) matching of a given cardinality. For a given k(L(G)) find a matching of cardinality k and maximum (minimum) possible weight sum.
Heaviest matching. Find a matching of maximum possible weigh sum. The complexity O(|V|3) for bipartite graphs and O(|V|4) in general case.

---
Some Discrete Optimization Problems
Maximum matching needs not to be the heaviest one and vice-versa.
Cardinality: 4
Weight: 4
1
10
1
1
1
1
1
1
1
10
1
1
1
1
1
1
Cardinality: 3
Weight: 12

---
Scheduling on Parallel Processors
to Minimize the Schedule Length
Identical processors, independent tasks
Preemptive scheduling P|pmtn|Cmax.
McNaughton Algorithm (complexity O(n))
1. Derive optimal length Cmax*=max{j=1,...,n pj/m, max j=1,...,n pj},
2. Schedule the consecutive tasks on the first machine until Cmax* is reached. Then interrupt the processed task (if it is not completed) and continue processing it on the next machine starting at the moment 0.
Example. m=3, n=5, p1,...,p5=4,5,2,1,2.
i=1,...,5 pi=14, max pi=5,
Cmax*=max{14/3,5}=5.
X* denotes the optimal value (i.e. the minimum possible value) of the parameter X, e.g. Cmax*, Lmax*.

---
Scheduling on Parallel Processors
to Minimize the Schedule Length
Identical processors, independent tasks
Non-preemptive scheduling P||Cmax.
The problem is NP–hard even in the case of two processors (P2||Cmax).
There exists an exact pseudo-polynomial dynamic-programming algorithm of complexity O(nCm), for some CCmax*.
Proof. Partition Problem: there is given a sequence of positive integers a1,...an, such that S=i=1,...,n ai. Determine if there exists a sub-sequence of sum S/2?
PP  P2||Cmax reduction: put n tasks of lengths pi=ai (i=1,...,n) and two processors. Determine if CmaxS/2.

---
Scheduling on Parallel Processors
to Minimize the Schedule Length
Identical processors, independent tasks
Non-preemptive scheduling P||Cmax.
Polynomial-time approximation algorithms.
List Scheduling LS – an algorithm used in numerous problems:
Fix an ordering of the tasks on the list,
Any time a processor gets free (a task processed by that processor has been completed), schedule the first available task from the list on that processor.
In the case of dependent tasks. Task Ti is available if all the tasks Tj it depends on
(i.e. TjTi) are completed.

---
Scheduling on Parallel Processors
to Minimize the Schedule Length
Identical processors, independent tasks
Non-preemptive scheduling P||Cmax.
Polynomial-time approximation algorithms.
List Scheduling LS – an algorithm used in numerous problems:
Fix an ordering of the tasks on the list,
Anytime a processor gets free (a task processed by that processor has been completed), schedule the first available task from the list on that processor.
Example. m=3, n=5, p1,...,p5=2,2,1,1,3.
List scheduling
Optimal scheduling

---
Scheduling on Parallel Processors
to Minimize the Schedule Length
Identical processors, independent tasks
Non-preemptive scheduling P||Cmax.
Polynomial-time approximation algorithms.
List Scheduling LS – an algorithm used in numerous problems:
Fix an ordering of the tasks on the list,
Anytime a processor gets free (a task processed by that processor has been completed), schedule the first available task from the list on that processor.
Approximation ratio: LS is 2–approximate: Cmax(LS)(2–m–1)Cmax*.
C *max(pmtn)  Cmax* 
 Cmax(LS)  i=1,...,k p(i)+i pi/m =
= (1–1/m)i=1,...,k p(i)+ i pi/m 
 (2–1/m)C *max(pmtn)(2–1/m) Cmax*
Proof (includes dependant tasks model P|prec|Cmax). Consider a sequence of tasks T(1),..., T(k) in a LS schedule, such that
T(1) – the last completed task, T(2) – the last completed predecessor of T(1) etc.

---
Scheduling on Parallel Processors
to Minimize the Schedule Length
Identical processors, independent tasks
Non-preemptive scheduling P||Cmax.
Polynomial-time approximation algorithms.
LPT (Longest Processing Time) scheduling:
List scheduling, where the tasks are sorted in non-increasing processing times pi order.
Approximation ratio. LPT is 4/3–aproximate:Cmax(LPT)(4/3–(3m)–1)Cmax*.
Unrelated processors, not dependent tasks
Preemptive scheduling R|pmtn|Cmax
Polynomial time algororihtm – to be discussed later ...
Non-preemptive scheduling R||Cmax
The problem is NP–hard (generalization of P||Cmax).
Subproblem Q|pi=1|Cmax is solvable in polynomial time.
LPT is used in practice.

---
Scheduling on Parallel Processors
to Minimize the Schedule Length
Identical processors, dependent tasks
Preemptive scheduling P|pmtn,prec|Cmax.
The problem is NP–hard.
P2|pmtn,prec|Cmax and P|pmtn,forest|Cmax are solvable in O(n2) time.
The following inequality estimating preemptive, non-preemptive and LS schedules holds
C*max C(LS) (2–m–1)C*max(pmtn)
Proof. The same as in the case of not dependent tasks.

---
Scheduling on Parallel Processors
to Minimize the Schedule Length
Identical processors, dependent tasks
Non-preemptive scheduling P|prec|Cmax.
Obviously the problem is NP–hard.
Many unit-time processing time cases are known to be solvable in polynomial time:
P|pi=1,in–forest|Cmax and P|pi=1,out–forest|Cmax (Hu algorithm, complexity O(n)),
P2|pi=1,prec|Cmax (Coffman–Graham algorithm, complexity O(n2)),
Even P|pi=1,opositing–forest|Cmax i P2|pi{1,2},prec|Cmax are NP–hard.
Hu algorithm:
out–forest  in–forest reduction: reverse the precedence relation. Solve the problem and reverse the obtained schedule.
in–forest  in–tree: add extra task dependent of all the roots. After obtaining the solution, remove this node from the schedule.
Hu algorithm sketch: list scheduling for dependent tasks + descending distance from the root order.

---
Scheduling on Parallel Processors
to Minimize the Schedule Length
Identical processors, dependent tasks
Non-preemptive scheduling
Hu algorithm (P|pi=1,in–tree|Cmax):
Level of a task – number of nodes in the path to the root.
The task is available at the moment t if all the tasks dependent of that task have been completed until t.
Compute the levels of the tasks;
t:=1;
repeat
Find the list Lt of the tasks available at the moment t;
Sort Lt in non-increasing levels order;
Assign m (or less) first tasks from Lt to the processors;
Remove the scheduled tasks from the graph;
t:=t+1;
until all the tasks are scheduled;

---
Scheduling on Parallel Processors
to Minimize the Schedule Length
Identical processors, dependent tasks
Non-preemptive scheduling
Example. Hu algorithm. n=12, m=3.
T1
T2
T3
T4
T5
T7
T6
T10
T9
T8
T11
T12
1
2
3
4
available tasks

---
Scheduling on Parallel Processors
to Minimize the Schedule Length
Identical processors, dependent tasks
Non-preemptive scheduling
Example. Hu algorithm. n=12, m=3.
T1
T2
T3
T4
T5
T7
T6
T10
T9
T8
T11
T12
1
2
3
4

---
Scheduling on Parallel Processors
to Minimize the Schedule Length
Identical processors, dependent tasks
Non-preemptive scheduling
Example. Hu algorithm. n=12, m=3.
T1
T2
T3
T4
T5
T8
T7
T6
T9
T11
T10
T12
1
2
3
4

---
Scheduling on Parallel Processors
to Minimize the Schedule Length
Identical processors, dependent tasks
Non-preemptive scheduling
Example. Hu algorithm. n=12, m=3.
T1
T2
T3
T4
T5
T8
T7
T6
T9
T11
T10
T12
1
2
3
4

---
Scheduling on Parallel Processors
to Minimize the Schedule Length
Identical processors, dependent tasks
Non-preemptive scheduling
Example. Hu algorithm. n=12, m=3.
T1
T2
T3
T4
T5
T8
T7
T6
T9
T11
T10
T12
1
2
3
4

---
Scheduling on Parallel Processors
to Minimize the Schedule Length
Identical processors, dependent tasks
Non-preemptive scheduling
Example. Hu algorithm. n=12, m=3.
T1
T2
T3
T4
T5
T8
T7
T6
T9
T11
T10
T12
1
2
3
4

---
Scheduling on Parallel Processors
to Minimize the Schedule Length
Identical processors, dependent tasks
Non-preemptive scheduling
Coffman–Graham algorithm (P2|pi=1,prec|Cmax):
label the tasks with integers l from the range [1 ... n],
list scheduling, with an ascending labels order.
Phase 1 – tasks labeling;
no task has any label or list at the beginning;
for i:=1 to n do begin
A:=the set of tasks without label, for which all dependent	tasks are labeled;
for each TA do assign the ascending sequence of the
labels of tasks dependent of T to list(T);
choose TA with the lexicographic minimum list(T);
l(T):=i;
end;

---
Scheduling on Parallel Processors
to Minimize the Schedule Length
Identical processors, dependent tasks
Non-preemptive scheduling
Example. Coffman–Graham algorithm, n=17.
1
10
5
16
(5)
12
6
3
(12,10)
14
9
4
17
13
(4,3,2)
8
2
(15,13)
15
(3,2)
(11,8)
7
11
(7)
(2)
T1
T3
T2
T4
T5
T6
T7
T9
T10
T8
T11
T12
T14
T17
T13
T15
T16
( )
( )
( )
( )
(1)
(1)
(9)
(9)
(9,6)

---
Scheduling on Parallel Processors
to Minimize the Schedule Length
Identical processors, dependent tasks
Non-preemptive scheduling
Example. Coffman–Graham algorithm, n=17.
1
10
5
16
The ordering in the list:
T2, T1, T7, T3, T6, T5, T12, T4, T10, T11, T16, T9, T8, T17, T14, T15, T13.
12
6
3
14
9
4
17
13
8
2
15
7
11
T1
T3
T2
T4
T5
T6
T7
T9
T10
T8
T11
T12
T14
T17
T13
T15
T16

---
Scheduling on Parallel Processors
to Minimize the Schedule Length
Identical processors, dependent tasks
Non-preemptive scheduling
LS heuristic can be applied to P|prec|Cmax. The solution is 2–approximate: Cmax(LS)(2–m–1)Cmax*.
Proof. It has been proved already ...
The order on the list (priority) can be chosen in many different ways. However, some anomalies may occur, i.e. the schedule may lengthen while:
increasing the number of processors,
decreasing the processing times,
releasing some precedence constraints,
changing the list order.

---
Scheduling on Parallel Processors
to Minimize the Mean Flow Time
Identical processors, independent tasks
Corollaries.
the processing time of the first task is multiplied by the greatest coefficient; the coefficients of the following tasks are decreasing,
to minimize Cj we should schedule short tasks first (as they are multiplied by the greatest coefficients),
list scheduling with the SPT rule (Shortest Processing Times) leads to an optimal solution on a single processor,
how to assign the tasks to the processors?
Proposal: task Tj scheduled in the k-th position on machine Mi increments the value of Cj by kpj (or kpij in the case of R|).

---
Scheduling on Parallel Processors
to Minimize the Mean Flow Time
Identical processors, independent tasks
Both preemptive and non-preemptive cases
The problems P||Ci and P|pmtn|Ci can be considered together (preemptions do not improve the criterion)
Optimal algorithm O(nlog n):
1. Suppose the number of tasks is a multiplicity of m (introduce empty tasks if needed),
2. Sort the tasks according to SPT,
3. Assign the following m–tuples of tasks to the processors arbitrarily.
Example. m=2, n=5, p1,...,p5=2,5,3,1,3.
SPT: T4 T1 T3 T5 T2
pi= 1 2 3 3 5
T0
0
Empty task

---
Scheduling on Parallel Processors
to Minimize the Mean Flow Time
Identical processors, independent tasks
Both preemptive and non-preemptive cases
The problems P||Ci and P|pmtn|Ci can be considered together (preemptions do not improve the criterion)
Optimal algorithm O(nlog n):
1. Suppose the number of tasks is a multiplicity of m (introduce empty tasks if needed),
2. Sort the tasks according to SPT,
3. Assign the following m–tuples of tasks to the processors arbitrarily.
Example. m=2, n=5, p1,...,p5=2,5,3,1,3.
SPT: T4 T1 T3 T5 T2
pi= 1 2 3 3 5
Cj*=21
T0
0
Empty task

---
Scheduling on Parallel Processors
to Minimize Mean Flow Time
Identical processors, independent tasks
Both preemptive and non-preemptive cases
The problems P||Ci and P|pmtn|Ci can be considered together (preemptions do not improve the criterion)
Optimal algorithm O(nlog n):
1. Suppose the number of tasks is a multiplicity of m (introduce empty tasks if needed),
2. Sort the tasks according to SPT,
3. Assign the following m–tuples of tasks to the processors arbitrarily.
Proof (the case of non-preemptive scheduling).
Lemma. Suppose a1,...,an i b1,...,bn are sequences of positive integers. How to permutate them in order to make the dot product
a(1)b(1)+a(2)b(2)+...+a(n–1)b(n–1)+a(n)b(n)
the greatest possible?
the smallest possible?
– both should be sorted in ascending order,
– sort one ascending, the second descending
Example. The sequences are (3,2,4,6,1) and (5,7,8,1,2).
(1,2,3,4,6) and (1,2,5,7,8)  1+4+15+28+48=96
(1,2,3,4,6) and (8,7,5,2,1)  8+14+15+8+6=51

---
Scheduling on Parallel Processors
to Minimize the Mean Flow Time
Identical processors, independent tasks
Both preemptive and non-preemptive cases
The problems P||Ci and P|pmtn|Ci can be considered together (preemptions do not improve the criterion)
Optimal algorithm O(nlog n):
1. Suppose the number of tasks is a multiplicity of m (introduce empty tasks if needed),
2. Sort the tasks according to SPT,
3. Assign the following m–tuples of tasks to the processors arbitrarily.
Proof (the case of non-preemptive scheduling). Consider some left-shifted scheduling. One may assume that there are k tasks scheduled on each processors (introducing empty tasks if needed).
Ci = kp(1)+...+kp(m) +
+(k–1)p(m+1) +...+(k–1)p(2m) + …
...+1p(km–m+1) +...+1p(km)
Reordering the tasks according to the SPT rule does not increase Ci.

---
Scheduling on Parallel Processors
to Minimize the Mean Flow Time
Identical processors, independent tasks
Non-preemptive scheduling
In the case the weights are introduced even P2||wjCj is NP–hard.
Proof (sketch) Similar to P2||Cmax. PP  P2||wiCi reduction: take n tasks with pj= wj=aj (j=1,...,n), two processors. There exists a number C(a1,...,an), such that wjCjC(a1,...,an)  Cmax*= i=1,...,n ai/2 (exercise).

---
Scheduling on Parallel Processors
to Minimize the Mean Flow Time
Identical processors, independent tasks
Non-preemptive scheduling
In the case the weights are introduced even P2||wjCj is NP–hard.
Proof (sketch) Similar to P2||Cmax. PP  P2||wiCi reduction: take n tasks with pj= wj=aj (j=1,...,n), two processors. There exists a number C(a1,...,an), such that wjCjC(a1,...,an)  Cmax*= i=1,...,n ai/2 (exercise).
Following Smith rule in the case of single processor scheduling (1||wjCj) leads to an optimal solution in O(nlog n) time:
sort the tasks in ascending pj/wj order.
Proof. Consider the improvement of the criterion caused by changing two consecutive tasks.
wjpj+wi(pi+pj) – wipi – wj(pi+pj) =
= wipj – wjpi  0  pj/wj  pi/wi
violating Smith rule increases wiCi .

---
Scheduling on Parallel Processors
to Minimize the Mean Flow Time
Identical processors, independent tasks
Non-preemptive tasks
RPT algorithm can be used in order to minimize both Cmax and Ci :
1. Use the LPT algorithm.
2. Reorder the tasks within each processor due to the SPT rule.
Approximation ratio: 1Ci (RPT)/Ci*m (commonly better)
Identical processors, dependent tasks
Even 1|prec|Ci, P|prec,pj=1|Ci, P2|prec, pi{1,2},|Ci,
P2|chains|Ci and P2|chains,pmtn|Ci are NP–hard.
Polynomial-time algorithms solving P|out–tree,pj=1|Ci (adaptation of Hu algorithm) and P2|prec,pj=1|Ci (Coffman–Graham) are known.
In the case of weighted tasks even single machine scheduling of unit time tasks 1|prec,pj=1|wiCi is NP–hard.

---
Scheduling on Parallel Processors
to Minimize the Mean Flow Time
Unrelated processors, independent tasks
O(n3) algorithm solving R||Ci is based on the problem of graph matching.
Bipartite weighted graph:
Partition V1 corresponding to the tasks T1,...,Tn.
Partition V2 – each processor n times: kMi, i=1...m, k=1...n.
The edge connecting Tj and kMi is weighted with kpij (it corresponds to scheduling Tj on Mi in the k–th position from the end.
We construct the lightest matching of n edges, which corresponds to optimal scheduling.
kpij
T1
Tj
Tn
1M1
1Mm
2M1
nMm
nM1
kMi
2
k
n
1

---
Scheduling on Parallel Processors
to Minimize the Maximum Lateness
Properties:
Di=max{Li,0}, so Dmax=max{Lmax,0} and Lmax–minimization contains Dmax–minimization,
Lmax* = the lowest possible x which can be added to all due dates (i.e. dj'=dj+x) to allow a lateness free schedule (i.e. with L'max≤0),
Both problems:
Lmax–minimization (...|...|Lmax),
no optimization criterion: tasks' dj are deadlines, check if it is possible to create a feasible schedule (...|...,Ci≤di|–),
are equally difficult.
Lmax criterion is a generalization of Cmax, the problems that are NP-hard in the case of minimizing Cmax remain NP-hard in the case of Lmax,
i.e. Lmax counted with new duedates dj'

---
Scheduling on Parallel Processors
to Minimize the Maximum Lateness
Properties:
scheduling on a single processor
if we have several tasks of different due times we should start with the most urgent one to minimize maximum lateness,
this leads to the EDD rule (Earliest Due Date) – choose tasks in the ordering of ascending due dates dj,
the problem of scheduling on a single processor (1||Lmax) is solved by using the EDD rule.

---
Scheduling on Parallel Processors
to Minimize the Maximum Lateness
Identical processors, independent tasks
Preemptive scheduling
Single machine: Liu algorithm O(n2), based on the EDD rule, solves 1|ri,pmtn|Lmax:
1. Choose the task of the smallest due date among available ones.
2. Every time a task has been completed or a new task has arrived go to 1. (in the latter case we preempt currently processed task).
Arbitrary number of processors (P|ri,pmtn|Lmax). A polynomial-time algorithm is known:
We use sub-routine solving the problem with deadlines P|ri,Cidi,pmtn|–. We find the optimal value of Lmax using binary search algorithm.

---
Scheduling on Parallel Processors
to Minimize the Maximum Lateness
We transform P|ri,Cidi,pmtn|– to the problem of maximum flow. First we put the values ri and di into the ascending sequence e0<e1<...<ek.
We construct a network:
The source is connected by k arcs of capacity m(ei–ei–1) to nodes wi, i=1,...,k.
The arcs of capacity pi connect nodes-tasks Ti to the sink, i=1,...,n.
We connect wi and Tj by an arc of capacity ei–ei–1, iff
[ei–1,ei][rj,dj].
A schedule exists  there exists a flow of value i=1,...,n pi (one can distribute the processors among tasks in the time intervals [ei-1, ei] to complete all the tasks).
m(e1–e0)
m(ei–ei–1)
S
T
w1
wi
wk
T1
Tj
Tn
m(ek–ek–1)
p1
pj
pn
e1–e0
ei–ei–1

---
Scheduling on Parallel Processors
to Minimize the Maximum Lateness
Dependent tasks
Non-preemptive scheduling
Some NP–hard cases: P2||Lmax, 1|rj|Lmax.
Polynomial-time solvable cases:
unit processing times P|pj=1,rj|Lmax.
similarly for uniform processors Q|pj=1|Lmax (the problem can be reduced to linear programming),
single processor scheduling 1||Lmax – solvable using the EDD rule
(has been discussed already...).

---
Scheduling on Parallel Processors
to Minimize the Maximum Lateness
Dependent tasks
Preemptive scheduling
Single processor scheduling 1|pmtn,prec,rj|Lmax can be solved by a modified Liu algorithm O(n2):
1. Determine modified due dates for each task:
dj*=min{dj, mini{di:TjTi}}
2. Apply the EDD rule using dj* values, preempting current task in the case a task with smaller modified due-date gets available.
3. Repeat 2 until all the tasks are completed.
Some other polynomial-time cases:
P|pmtn,in–tree|Lmax, Q2|pmtn,prec,rj|Lmax.
Moreover, some pseudo-polynomial time algorithms are known.

---
Scheduling on Parallel Processors
to Minimize the Maximum Lateness
Dependent tasks
Non-preemptive scheduling
Even P|pj=1,out–tree|Lmax is NP–hard.
A polynomial-time algorithm for P2|prec,pj=1|Lmax is known.
P|pj=1,in–tree|Lmax can be solved by Brucker algorithm O(nlog n):
next(j) = immediate successor of task Tj.
1. Derive modified due dates: droot*=1–droot for the root and dk*=max{1+dnext(k)*,1–dk} for other tasks
2. Schedule the tasks in a similar way as in Hu algorithm, choosing every time the tasks of the greatest modified due date instead of the greatest distance from the root.
The list scheduling again with a different ordering of the tasks again.

---
Scheduling on Parallel Processors
to Minimize the Maximum Lateness
Dependent tasks
Non-preemptive scheduling
Example. Brucker algorithm, n=12, m=3, due dates in the nodes.
4
6
4
2
3
T1
T2
T3
T4
T5
1
5
3
1
T8
T7
T6
T9
6
3
T11
T10
-6
7
T12
-5,-5
-2,-5
0,-4
-4,-4
-2,-1
0,-1
-3,-3
-5,-3
-3,0
-1,1
-2,1

---
Scheduling on Parallel Processors
to Minimize the Maximum Lateness
Dependent tasks
Non-preemptive scheduling
Example. Brucker algorithm, n=12, m=3, due dates in the nodes.
4
6
4
2
3
T1
T2
T3
T4
T5
1
5
3
1
T8
T7
T6
T9
6
3
T11
T10
7
T12
-6
-5
-2
0
-4
-1
0
-3
-3
0
1
1

---
Scheduling on Parallel Processors
to Minimize the Maximum Lateness
Dependent tasks
Non-preemptive scheduling
Example. Brucker algorithm, n=12, m=3, due dates in the nodes.
T1
T2
T3
T4
T5
T8
T7
T6
T9
T11
T10
T12
-6
-5
-2
0
-4
-1
0
-3
-3
0
1
1

---
Scheduling on Parallel Processors
to Minimize the Maximum Lateness
Dependent tasks
Non-preemptive scheduling
Example. Brucker algorithm, n=12, m=3, due dates in the nodes.
T1
T2
T3
T4
T5
T8
T7
T6
T9
T11
T10
T12
-6
-5
-2
0
-4
-1
0
-3
-3
0
1
1

---
Scheduling on Parallel Processors
to Minimize the Maximum Lateness
Dependent tasks
Non-preemptive scheduling
Example. Brucker algorithm, n=12, m=3, due dates in the nodes.
T1
T2
T3
T4
T5
T8
T7
T6
T9
T11
T10
T12
-6
-5
-2
0
-4
-1
0
-3
-3
0
1
1

---
Scheduling on Parallel Processors
to Minimize the Maximum Lateness
Dependent tasks
Non-preemptive scheduling
Example. Brucker algorithm, n=12, m=3, due dates in the nodes.
T1
T2
T3
T4
T5
T8
T7
T6
T9
T11
T10
T12
-6
-5
-2
0
-4
-1
0
-3
-3
0
1
1

---
Scheduling on Parallel Processors
to Minimize the Maximum Lateness
Dependent tasks
Non-preemptive scheduling
Example. Brucker algorithm, n=12, m=3, due dates in the nodes.
T1
T2
T3
T4
T5
T8
T7
T6
T9
T11
T10
T12
-6
-5
-2
0
-4
-1
0
-3
-3
0
1
1

---
Scheduling on Parallel Processors
to Minimize the Maximum Lateness
Dependent tasks
Non-preemptive scheduling
Example. Brucker algorithm, n=12, m=3, due dates in the nodes.
T1
T2
T3
T4
T5
T8
T7
T6
T9
T11
T10
T12
-6
-5
-2
0
-4
-1
0
-3
-3
0
1
1

---
Scheduling on Parallel Processors
to Minimize the Maximum Lateness
Dependent tasks
Non-preemptive scheduling
Example. Brucker algorithm, n=12, m=3, due dates in the nodes.
4
6
4
2
3
T1
T2
T3
T4
T5
1
5
3
1
T8
T7
T6
T9
6
3
T11
T10
7
T12
-1
-1
0
Lmax*=1
-1
-1
1
-1
-3
-3
-1
-2
Lateness:

---
Minimizing the Number of Tardy Tasks
on a Single Machine
Independent non-preemptive tasks
Obviously even P2||Ui and P2||Di are NP-hard.
Proof. Similar to P2||Cmax.
Further we consider single processor scheduling only.

---
Minimizing the Number of Tardy Tasks
on a Single Machine
Independent non-preemptive tasks
Obviously even P2||Ui and P2||Di (and even 1||Di) are NP-hard.
Proof. Similar to P2||Cmax.
Further we consider single processor scheduling only.
Minimizing number of tardy tasks 1||Ui is polynomial-time solvable
Hodgson algorithm O(nlog n):
Sort the tasks with the EDD rule: T(1), T(2),...,T(n);
A:=;
for i:=1 to n do begin
A:=A{T(i)};
if ZjA pj>d(i) then remove the longest task from A;
end;
A – maximum cardinality set of tasks that can be scheduled on time.

---
Minimizing the Number of Tardy Tasks
on a Single Machine
Independent non-preemptive tasks
Obviously even P2||Ui and P2||Di (and even 1||Di) are NP-hard.
Proof. Similar to P2||Cmax.
Further we consider single processor scheduling only.
Minimizing number of tardy tasks 1||Ui is polynomial-time solvable
Hodgson algorithm O(nlog n):
Sort the tasks with the EDD rule: T(1), T(2),...,T(n);
A:=;
for i:=1 to n do begin
A:=A{T(i)};
if ZjA pj>d(i) then remove the longest task from A;
end;
A – maximum cardinality set of tasks that can be scheduled on time.
Schedule A in the EDD order, then the rest of the tasks in any order;

---
Minimizing the Number of Tardy Tasks
on a Single Machine
Independent non-preemptive tasks
Weighted tasks scheduling 1||wiUi is NP–hard as a generalization of knapsack problem.
Assuming unit execution times makes these problems easier: P|pj=1|wiUi i P|pj=1|wiDi are polynomial time solvable – a natural reduction to the problem of lightest matching in a bipartite graph.

---
Minimizing the Number of Tardy Tasks
on a Single Machine
Dependent and non-preemptive tasks
NP-hardness even with unit processing times for the problems 1|pj=1,prec|Ui and 1|pj=1,prec|Di.
Proof. Clique problem: for a given graph G (V,E) and a positive integer k determine if G contains a complete subgraph of k vertices.
CP  1|pj=1,prec|Ui reduction: We put unit processing time tasks Tv with
dv=|VE| for every vertex vV and Te with de=k+k(k–1)/2 for every edge eE. Precedence constraints: Tv  Te  v is incident to e. Limit L=|E|–k(k–1)/2.
Example. k=3
a
b
c
d
Ta
Tb
Tc
Td
T{a,b}
T{a,c}
T{b,c}
T{c,d}
di=8
di=6
L=1

---
Minimizing the Number of Tardy Tasks
on a Single Machine
Dependent and non-preemptive tasks
NP-hardness even with unit processing times for the problems 1|pj=1,prec|Ui and 1|pj=1,prec|Di.
Proof. Clique problem: for a given graph G (V,E) and a positive integer k determine if G contains a complete subgraph of k vertices.
CP  1|pj=1,prec|Ui reduction: We put unit processing time tasks Tv with
dv=|VE| for every vertex vV and Te with de=k+k(k–1)/2 for every edge eE. Precedence constraints: Tv  Te  v is incident to e. Limit L=|E|–k(k–1)/2.
In a similar way CP  1|pj=1,prec|Di reduction.
All the tasks are completed until |VE| in any optimal solution. Thus, whenever UiL, at least k(k–1)/2 tasks Te are completed until k+k(k–1)/2. Therefore the corresponding edges are incident with at least k vertices (for which the tasks Tv precede Te). That is possible only in the case these k vertices form a clique.

---
Minimizing the Number of Tardy Tasks
on a Single Machine
Parallel processors, minimizing Cmax again
We have constructed a reduction PK  1|pj=1,prec|Ui. In a similar way NP–hardness of P|pj=1,prec|Cmax can be proved.
If Cmax*=3 then:
All the gray-colored parts are fulfilled with Tv and Te,
In the 1st time unit only Tv are scheduled, in the 3rd time unit only Te are scheduled,
In the 2nd time unit k(k–1)/2 tasks Te are processed and the corresponding edges are incident to k vertices, which form a clique (corresponding tasks are processed in the first time unit).
Proof. Clique Problem: for a given graph G (V,E) and a positive integer k determine if G contains a complete subgraph of k vertices.
CP  P|pj=1,prec|Cmax reduction: unit time tasks Tv for each vV and Te for each eE. Precedence constraints: Tv  Te  v is incident to e. Limit L=3. Moreover, 3 'levels' of unit tasks TA1,TA2,...  TB1,TB2,...
 TC1,TC2,... The number of processors m big enough to
make Cmax=3 possible: